## TOC Query
NO | PROJECT | Project Limits | Project Scope | Estimated Cost | START DATE | COMPLETION DATE | PM
1 | Patterson Ave @ St. Christopher's Rd New Traffic Signal | Patterson Ave @ St. Christopher's Rd | Install a new traffic signal control device. | 700000 | Fall 2025 | Spring 2026 | Coggins
2 | Systemic Improvements - Stop Controlled Intersections | Citywide | To replace the regulatory and warning signs and pavement marking at 200 stop controlled intersections. | 3478000 | Winter 2026 | Winter 2027 | Anwari
3 | Systemic Improvements - Left Turn Lane Hardening | Citywide | To install left turn hardening at stop control intersections | 1285000 | Winter 2026 | Winter 2027 | Anwari
4 | SR 147 Main Street Pedestrian Safety | Main St between Belvidere St and Arthur Ashe Blvd. | To improve pedestrian safety along State Route 147 (Main Street) by constructing pedestrian safety curb extensions, mainly on the upstream side of the cross streets. | 595000 | TBD | Summer 2026 | Famili
5 | Speed Feedback Management Program | Citywide | To enhance roadway safety by reducing vehicular speeds through the use of speed feedback signs | 1100000 | TBD | Summer 2026 | Famili
6 | Smart Cities: Centralized Transit Signal Priority (TSP)/Emergency Vehicle Preemption (EVP) Project | Various locations Citywide. | Centralized software system to manage Transit Signal Priority (TSP) and Emergency Vehicle Preemption (EVP) requests and authorizations at City traffic signals. | 4781000 | Summer 2025 | Summer 2027 | Burgos
7 | Safe Streets for All (SS4A) | City wide | Installing the following traffic controls: 1) High Visibility Backplates for 9 intersections. 2) Flashing yellow Arrows at 12 intersections . 3) Pedestrian Hybrid Beacons at 6 intersections. 4) Improve 88 unsignalized intersections. 5) Harden left turn movement for 25 intersections. 6) Harden 2-miles of Bike Lanes. 7) Improve Transit ADA accessibility at 78 transit stops. 8) Replace street lighting with LED street lighting for 400 intersections | 13500000 | Fall 2026 | Summer 2029 | Hanna
8 | Richmond Signal System Phase IV | Various locations at the northeastern area of the City. | Expansion of the traffic signal communication network to the northeast area of the City. | 5788000 | Spring 2025 | Winter 2027 | Burgos
9 | Richmond Signal System (RSS) Smart City Traffic Signals Controllers | Various locations Citywide. | Replace around 300 obsolete\aging traffic signal controllers and around 70 traffic signal cabinets. | 7300000 | Fall 2027 | Winter 2028 | Burgos
10 | Pedestrian Hybrid Beacon (PHB) Hull St @ 29th St | Hull St @ 29th St | Install a new PHB and ADA-accessible curb ramps, and refresh or install pavement markings. | 554000 | Winter 2025 | Winter 2026 | Anwari
11 | Patterson Avenue Bike Lanes | Patterson Avenue between Commonwealth Avenue and Willow Lawn Drive | To provide the installation of pavement markings and signs to provide on-street buffered bike lanes along Patterson Avenue. | 765000 |  | Summer 2027 | Boyce
12 | Patterson Ave @ Pepper Ave New Traffic Signal | Patterson Ave @ Pepper Ave | Install a new traffic signal control device. | 650000 | Winter 2025 | Fall 2025 | Coggins
13 | Patterson Ave (Libbie & Westview) Traffic Signal Improvements | Patterson Ave @ Libbie Ave Patterson Ave @ Westview Ave | Upgrade existing traffic signal infrastructure, install ADA-accessible curb ramps, and refresh or install pavement markings. | 1500000 | Spring 2027 | Summer 2028 | Burgos
14 | Malvern Ave @ Cary St Traffic Signal Improvements | Malvern Ave @ Cary St | Upgrade existing traffic signal infrastructure, install ADA-accessible curb ramps, and refresh or install pavement markings. | 500000 | Fall 2025 | Spring 2026 | Coggins
15 | HVSB Systemic Improvements - Signal Controlled Intersections | City wide | Installing the following traffic controls: 1) High Visibility Backplates at 170 intersections. 2) Flashing Yellow Arrows at 29 intersections . 3) High Visibility Crosswalks at 58 intersections. | 6000000 | Summer 2026 | Summer 2029 | Hanna
16 | Hull Street Road Diet from McGuire Drive to Midlothian Turnpike | Hull St from McGuire Drive to Midlothian Turnpike | To provide the installation of pavement markings and signs to provide roadway reconfiguration along project limits. | 680000 | Spring 2026 | Summer 2026 | Anwari
17 | Forest Hill Avenue Bike / Pedestrian Improvements | Forest Hill Ave at 41st and Forest Hill Ave at 43rd Intersections | To install new RRFBs and hardening the buffer at the intersection of 41st and 43rd Streets in order to improve pedestrian and bicycle safety. | 750000 |  | Summer 2026 | Famili
18 | F Roadway Conversions - Citywide Phase II | Hopkins Rd between Richmond Highway (Rte 301) and Collier Hill Road | To provide the installation of pavement markings and signs to provide on-street buffered bike lanes along the Hopkins Road corridor. | 2308000 |  | Fall 2026 | Famili
19 | Cary St @ Commonwealth Ave Pedestrian Hybrid Beacon (PHB) | Cary St at Commonwealth Ave intersection | Install a new PHB and ADA-accessible curb ramps, and refresh or install pavement markings. | 270000 | Winter 2025 | Winter 2026 | Anwari
20 | Cary St (Rte. 147) Pedestrian Improvement(Ph II) | Cary St between Belvidere St and Arthur Ashe Blvd. | To improve pedestrian safety along State Route 147 (Cary Street) by constructing pedestrian safety curb extensions, mainly on the upstream side of the cross streets. | 650000 |  | Summer 2026 | Famili
21 | Brook Rd @ Westbrook Ave Traffic Signal Improvements | Intersection of Brook Rd @ Westbrook Ave | Upgrade existing traffic signal infrastructure, install ADA-accessible curb ramps, and refresh or install pavement markings. | 600000 | Spring 2026 | Summer 2026 | Adel
22 | Brook Rd @ Azalea Ave Traffic Signal Upgrade Project | Brook Rd @ Azalea | Upgrade existing traffic signal infrastructure, install ADA-accessible curb ramps, and refresh or install pavement markings. | 750000 | Fall 2027 | Summer 2028 | Burgos
23 | Automated Traffic Signal Performance Measures (ATSPM) | Citywide | This project will leverage the existing traffic signal communication network to implement the open-source FHWA ATSPM software to aggregate high-resolution traffic signal controller data into performance measures for up to 145 City traffic signals along 17 corridors. | 6849000 | Fall 2026 | Winter 2028 | Adel
24 | 7th St @ Hospital St New Traffic Signal | 7th St @ Hospital | Install a new traffic signal control device. | 1250000 | Summer 2029 | Summer 2030 | Burgos
25 | 32nd St @ Midlothian Tpke | 32nd St @ Midlothian Tpke | Upgrade existing traffic signal infrastructure, install ADA-accessible curb ramps, and refresh or install pavement markings. | 600000 | Winter 2025 | Fall 2025 | Coggins
26 | 21st St @ Main St Traffic Signal Upgrade | Main St @ 21st Street | Upgrade existing traffic signal infrastructure, install ADA-accessible curb ramps, and refresh or install pavement markings. | 420000 | Spring 2024 | Summer 2025 | Adel
27 | 2026 Citywide paving |  |  |  | TBD | Summer 2026 | Horak
28 | SGR Paving Commerce Rd 2 |  |  |  | TBD | Winter 2025 | Horak
29 | SGR Paving Commerce Rd | Heat Scarification / Slurry Citywide |  |  | Summer 2025 | Summer 2026 | Horak
30 | SGR Paving Bells Rd | 1 inch mill and overlay Citywide | Mill and overlay streets and perform ADA up grades |  | Summer 2025 | Summer 2026 | Horak
31 | SGR Paving Broad Rock Rd | 2 inch mill and overlay citywide | Mill and overlay streets and perform ADA up grades |  | Summer 2025 | Summer 2026 | Horak
32 | Shockoe Valley Streets Improvement Project | Shockoe Valley Area (bounded by Broad Street interchange with I-95. Broad Street, Oliver Hill,Venable Street, Mosby Street, Martin Luther King Bridge, 8th Street from Balding to Broad Street) | Roadway improvements to include roundabouts, traffic signal upgrades, new sidewalks, crosswalks, landscaping pedestrian lighting. | 54000000 | Fall 2027 | Fall 2030 | Edward
33 | Scott's Addition Green Space | Along a portion of Patton Avenue, south of the CSX rail line between Roseneath Road and North Boulevard. | provide multi use path | 1106000 | Fall 2026 | Fall 2027 | Bruce
34 | Scotts Addition BRT Street Scape Project | Various locations within the half-mile walkshed of the BRT station. | Provide sidewalk, ADA accessible ramps and other pedestrian and streetscape amenities | 1612000 | Fall 2026 | Fall 2027 | Bruce
35 | Riverfront New Orleans BRT | Various locations within the half-mile walkshed of the BRT station. | pedestrian access and safety to the East Riverfront and Orleans BRT Stations by constructing sidewalk, ADA accessible ramps, and pedestrian and streetscape | 2057000 | Summer 2029 | Summer 2031 | Bruce
36 | Richmond Highway Phase II | Hull St. to Maury St. | Bike, Pedestrain and transit improvements | 13242000 | Spring 2029 | Spring 2031 | Phillips
37 | Richmond Highway - Rte 1 Intersection Improvement Harwood/Hopkins | Harwood to Hopkins | sidewalk, ramps, new traffic signal, drainage improvements | 12400000 | Fall 2024 | Fall 2026 | Phillips
38 | Richmond Henrico Turnpike | From Fourquean Drive to Dove Street | Installation of guardrail with shoulder widening | 3400000 | summer 2026 | Fall 2028 | Edward
39 | North Patterson Ave | Granite Ave. to Glenburnie Rd | Improvements to sidewalk, entrances, & crosswalks along Westbound lane | 205000 | Fall 2025 | Winter 2025 | Moore
40 | Nicholson Street Streetscape | East Main St to Williamsburg Ave | Addition of new streetside parking and sidewalk to Eastbound lane. Improvements to landscaping, pedestrian acess, and lighting. | 840000 | Spring 2027 | Spring 2028 | Moore
41 | Maury StreetScape Project | I-95 interchange to Commerce RD | Provide sidewalk, curb extensions, ADA ramps, lanscaping and other streetscape improvements | 4618000 | Winter 2029 | Winter 2030 | Bruce
42 | Martin Luther King Bridge Repairs | Leigh St from 12th St to Mosby St | Targeted Bridge repairs on the MLK bridge | 5700000 | Summer 2025 | Spring 2027 | Westbrook
43 | Manchester Connection to James River | T. Potterfield Br to Commerce Rd | Widen bridge over NSRR, and widen trail from Floodwall parking to T. Potterfield Br behind Costar | 6345000 | Winter 2028 | Spring 2029 | Westbrook
44 | Lynhaven Ave over Broad Rock Creek Bridge Replacement | Lynhaven Ave at Dallas Ave | Bridge Replacement | 3000000 | Fall 2025 | Winter 2026 | Westbrook
45 | Lombardy St over CSX Bridge replacement | Leigh St to School St | Replace bridge, enhance bike and pedestrain facilities | 21000000 | Winter 2027 | Spring 2028 | Westbrook
46 | Leigh Street Streetscape | 7th St to 12th St. | provide streetscape improvements | 6608000 | Summer 2026 | Spring 2028 | Wang
47 | Kanawha Plaza Pedestrain Safety Project | Byrd & Canal from 7th to 9th & 7th & 9th from Byrd to Canal | provide safety improvements for pedestrian | 3309000 | Spring 2026 | Spring 2027 | Wang
48 | Jefferson Ave. Improvements -Phase III & Phase IV | Leigh to 21st Street | provide sidewalk, curb extensions, ADA ramps, lanscaping and drainage improvements | 5900000 | Summer 2026 | Winter 2028 | Wang
49 | Jahnke Road Improvement | Blakemore to Forest Hill Ave. | Project provides complete streets mprovemnts to include a shared use path, bike lanes, sidewalks, raised median, landscaping, drainage improvements and signal modifications | 37000000 | Fall 2025 | Fall 2027 | Phillips
50 | Hull Street Streetscape | 9th St. to Mayo Bridge | provide pedestrian accommodations, improve landscaping/lighting | 4100000 | Spring 2026 | Winter 2027 | Phillips
51 | Hull Street Improvements - Phase I | From Hey Rd to Warwick Road | Project will consist of a raised median, turn lanes, curbs, gutters, bike lanes, new sidewalk and shared use path on the north side of Hull Street and new sidewalks on the south side of Hull Street, street lighting and an underground drainage system. The project will also improve access management along the corridor and will coordinate signal timings, thus providing a multi-modal transportation corridor. | 38000000 | Spring 2025 | Spring 2027 | Edward
52 | Hull St over Manchester Canal | Manchester Rd to E. 1st St | Bridge Replacement | 10775000 | Fall 2026 | Summer 2028 | Westbrook
53 | Hey Road Improvements | Hull St. to Walmsley Blvd | Improvements include constructing wider travel lanes, curb and gutter, sidewalk, utility relocations, and a closed drainage system. | 18270000 | Spring 2029 | Spring 2031 | Phillips
54 | Gillies Creek Greenway Phase I | Main St and Williamsburg Road | Provide a 10’ paved path, street crossing improvements at Main Street and at Williamsburg Avenue, roadway lighting improvements at Williamsburg Avenue, Government Road, and Jennie Scher Road, and bike, pedestrian and transit access improvements at eight transit stops/stations. | 5400000 | Summer 2027 | TBD | Edward
55 | Fall Line Trail Walmsley to Bellemeade | From Walmsley Blvd to Bellemeade Road | Construction of Shared Use Path | 6000000 | Summer 2027 |  | Edward
56 | E. Richmond Rd Bridge over Stoney Run Bridge Replacement | Jennie Scheer Rd to City Line | Bridge Replacement | 4100000 | Spring 2025 | Fall 2026 | Westbrook
57 | E. Richmond Rd Bridge over Gillies Crk Bridge Replacement | Jennie Scheer Rd to City Line | Bridge Replacement | 4100000 | Spring 2025 | Fall 2026 | Westbrook
58 | E. Broad St Bridge over Abandoned RR spur | I-95 to N. 16th St | Bridge Replacement | 4500000 | Spring 2026 | Winter 2027 | Westbrook
59 | E Main St./Williamsburg Ave. Intersection Improvement | Intersection of E Main Street & Williamsburg Road | Intersection realignment | 4500000 | Summer 2025 | Summer 2026 | Phillips
60 | Deepwater Terminal Road Connector to Goodes Street | Deepwater Terminal Road 0.69 miles north to Goodes Street | Roadway extenstion project | 7500000 | Summer 2026 | Spring 2027 | Edward
61 | Commerce Road Improvement | Bellemeade Rd to Bells Rd | Project provides roadway improvements to include a sidewalks, raised median, landscaping, drainage improvements and installation of a new bridge | 36319000 | Fall 2023 | Spring 2026 | Westbrook
62 | Commerce Rd fall Line Trail phase I | from the Manchester Bridge to Decatur Street | Safety and operational improvements through access management, turn lane improvements, bike lanes, sidewalks, shared-use paths, and other streetscape amenities. | 6400000 | Spring 2027 | TBD | Edward
63 | Columbia St over Goodes Creek structure replacement | Chesterman Ave to Mimosa St | Replace Culvert | 4000000 | Spring 2024 | Fall 2026 | Westbrook
64 | Chimborazo Park Sidewalks | N 33rd St. to Chimborazo Blvd | Installation of new sidewalk along Eastbound land of E Broad St; Improvements to pedestrian crossings of E Broad St. | 317000 | Summer 2025 | Fall 2025 | Moore
65 | Carnation Street Sidewalks - Phase 2 | Warwick Rd to Hioaks Rd | Installation of new sidewalk along both sides of Carnation St. | 543000 | Fall 2026 | Summer 2027 | Moore
66 | BRT Shockoe Bottom | Shockoe Bottom Area | Construct Sidewalks, ADA ramps, and other pedestrian and Streetscape amenities within the half mile walkshed of the BRT stations at Shockoe Bottom area. | 4900000 | Spring 2027 | Fall 2028 | Wang
67 | Brown's Island Connector -Phase III | Tredegar St. to T. Tyler Potterfield Memorial Bridge | Construct (ADA Compliant) access ramp improvements on Browns Island | 623000 | Fall 2025 | Summer 2026 | Phillips
68 | BLVD Shared Use Path to Science Museum BRT Station | Robinson St. BRT Station to Scott's Addition | Provide a paved Shared Use Path | 3278070 | Fall 2029 | Fall 2030 | Wang
69 | Biotech Phase 3 | Leigh St. from 7th. To 12th St. | Streetscape improvements | 336000 | Summer 2026 | Spring 2028 | Wang
70 | Bainbridge Street Sidewalks | W 30th St. to W 28th St. | Installing new sidewalk allong Eastbound lane of Bainbridge St | 121000 | Summer 2025 | Summer 2025 | Moore
71 | Arthur Ashe Blvd Bridge Replacement | Norfolk St. to Avenue of Champions | Replacement of the Arthur Ashe Blvd. Bridge | 38000000 | Winter 2026 | Winter 2029 | Wang
72 | Broad St. Streetscape w/Pulse BRT Expansion- Phase II | Hamilton Ave. to Commonwealth Ave. | 2 new BRT curbside stations, sidewalk, ADA ramps, and pedestrian crossing improvements | 27000000 | Spring 2029 | Spring 2031 | Wang
73 | Kanawha Plaza - Fall Line Trail | Kanawha Plaza from 9th& Byrd to 7th & Canal | provide multi use path | 4500000 | Fall 2028 | Fall 2029 | Wang
74 | Cary St. Sidewalk Improvements | Cary St @ Three Chopt Road | install pedestrain infrastructure along Cary St at the intersection of Three Chopt Road | 590000 | Fall 2026 | Spring 2027 | Wang
75 | Government Road Slope Repair | Chimborazo Park to Government Rd area | Slope stabilization project | 9300000 | Fall 2025 | Fall 2027 | Phillips
76 | Gillies Creek Greenway Phase IV | Jennie Scher Road from the intersection of Stony Run Road to E. Richmond Road | Construction of a shared-use path adding about 0.45 miles of dedicated bike and pedestrian infrastructure to the existing greenway. | 1500000 | Winter2026 | TBD | Benomar
77 | Hull Street Improvements - Phase II | From Chipenham to Hey Road | including a raised median, turn lanes, curbs, gutters, bike lanes, new sidewalk and shared use path on the north side of Hull Street and new sidewalks on the south side of Hull Street, street lighting and an underground drainage system | 17500000 | Summer 2027 | TBD | Edward
78 | Hull Street Improvements - Phase III | From Warwick Road to Arizona Avenue | including a raised median, turn lanes, curbs, gutters, bike lanes, new sidewalk and shared use path on the north side of Hull Street and new sidewalks on the south side of Hull Street, street lighting and an underground drainage system | 19000000 | Summer 2027 | TBD | Edward
79 | Clay Street Streetscape | Arthur Ashe Boulevard and Belleville Street | Street Conversion | 18720000 | TBD | TBD | Lewis
80 | Fall Line Trail - Transit Lanes | 0.9 mile stretch of Commerce Road and 9th Street (Manchester Bridge) between Perry Street and Byrd Street | Providing a 14’ continuous shared use path within a widened median as part of the regional 43-mile Fall Line Trail. This project will also provide dedicated transit-only lanes, bicycle and pedestrian access improvements and crossing accommodations. | 28300000 | TBD | TBD | Lewis